## GRC Risk Register
GRC RISK REGISTER — KTECH
Organisation: KTECH ¦ Sector: SaaS / Cloud Technology ¦ Regulated by: ICO, FCA (payments) ¦ Attestations: SOC 2 Type II, ISO 27001 ¦ Framework: ISO 31000 / NIST CSF ¦ Version: 1.0 ¦ Last Updated: 07 April 2026 ¦ Classification: Portfolio Demonstration
RISK IDENTIFICATION |  |  | DOMAIN & OWNERSHIP |  | INHERENT RISK ← AUTO |  |  |  | CONTROL ENVIRONMENT |  |  | RESIDUAL RISK ← AUTO |  |  |  | TREATMENT & TRACKING |  |  | AUDIT / REVIEW
Risk ID | Risk Title | Risk Description | Risk Domain | Risk Owner (Role) | Likelihood (1–5) | Impact (1–5) | Inherent Score ⚡ | Inherent Rating ⚡ | Control Description | Control Effectiveness | Control Owner (Role) | Residual Likelihood | Residual Impact | Residual Score ⚡ | Residual Rating ⚡ | Treatment Action | Accountable Role | Target Date | Last Review Date | Review Status
TC-001 | Inadequate Enterprise Risk Governance | No formal ERM framework means risks are managed in silos, creating blind spots and delayed executive response. | Governance | Chief Risk Officer (CRO) | 3 | 4 | 12 | High | Risk committee established; quarterly risk reporting; risk appetite statement drafted. | Basic | Chief Risk Officer (CRO) | 3 | 3 | 9 | Medium | Formalise ERM framework; appoint risk champions per business unit; launch risk culture survey. | Chief Risk Officer (CRO) | 2026-06-30 | 2025-11-01 | In Progress
TC-002 | Cloud Infrastructure Failure | Outage of primary cloud provider (AWS/Azure/GCP) causes platform downtime, SLA breach and revenue loss. | Information Technology | IT Director | 3 | 5 | 15 | High | Multi-AZ deployment; automated failover; 99.9% SLA with cloud provider; monthly DR tests. | Strong | IT Director | 1 | 5 | 5 | Low | Implement multi-region active-active architecture; quarterly failover drills; chaos engineering. | IT Director | 2026-06-30 | 2025-12-01 | In Progress
TC-003 | Software Supply Chain Attack | Malicious code injected into open-source dependencies or CI/CD pipeline compromises production systems. | Information Technology | Chief Information Security Officer (CISO) | 3 | 5 | 15 | High | SBOM generated for major releases; Dependabot alerts active; SCA tooling in CI pipeline. | Adequate | Chief Information Security Officer (CISO) | 2 | 5 | 10 | Medium | Mandate SBOM for all releases; deploy Sigstore signing; conduct supply chain risk assessment. | Chief Information Security Officer (CISO) | 2026-04-30 | 2025-11-15 | Open
TC-004 | Zero-Day Vulnerability Exploitation | Unknown vulnerability in product or infrastructure exploited before patch available, causing data breach. | Information Technology | Chief Information Security Officer (CISO) | 3 | 5 | 15 | High | Bug bounty programme active; WAF deployed; 24/7 SIEM monitoring; threat intelligence feeds. | Adequate | Chief Information Security Officer (CISO) | 2 | 4 | 8 | Medium | Reduce mean time to detect to <4hrs; integrate threat intel into SOAR; expand bug bounty scope. | Chief Information Security Officer (CISO) | 2026-05-31 | 2025-10-20 | Open
TC-005 | Customer Data Breach (GDPR/CCPA) | Unauthorised access to customer PII triggers regulatory fines, customer churn and reputational damage. | Information Technology | Data Protection Officer (DPO) | 3 | 5 | 15 | High | Encryption at rest & in transit; RBAC enforced; DLP tooling deployed; DPO appointed. | Adequate | Data Protection Officer (DPO) | 2 | 4 | 8 | Medium | Implement data discovery & classification; complete Article 30 records; conduct DPIA for AI features. | Data Protection Officer (DPO) | 2026-05-15 | 2025-12-01 | In Progress
TC-006 | Privileged Access & Insider Threat | Excessive or unchecked privileged access exploited by insiders or compromised admin accounts. | Information Technology | Chief Information Security Officer (CISO) | 3 | 4 | 12 | High | PAM solution deployed for 70% of critical systems; MFA enforced for all admin accounts. | Adequate | IT Director | 2 | 3 | 6 | Medium | Full PAM rollout; enforce JIT access; complete quarterly privileged access reviews. | IT Director | 2026-07-31 | 2025-09-01 | In Progress
TC-007 | Developer Talent Attrition | Loss of senior engineers and scarce AI/ML talent to competitors disrupts product roadmap and innovation capacity. | Human Resources | Chief People Officer (CPO) | 4 | 4 | 16 | High | Retention bonuses for key engineers; career ladder framework; quarterly engagement surveys. | Basic | Chief People Officer (CPO) | 3 | 4 | 12 | High | Introduce technical career progression tracks; publish engineering brand externally; benchmark comp annually. | Chief People Officer (CPO) | 2026-06-30 | 2025-10-01 | Open
TC-008 | AI / ML Skills Gap | Inability to hire or upskill staff in generative AI, MLOps and data science limits product competitiveness. | Human Resources | Chief People Officer (CPO) | 3 | 4 | 12 | High | Learning budget of £3K/head; partnerships with 2 universities; internal AI guild active. | Basic | Chief People Officer (CPO) | 3 | 3 | 9 | Medium | Launch AI upskilling programme; partner with bootcamps; establish internal AI Centre of Excellence. | Chief People Officer (CPO) | 2026-09-30 | 2025-11-01 | Open
TC-009 | Remote Work Security & Culture Risk | Distributed workforce increases insider threat surface, erodes culture and creates inconsistent security practices. | Human Resources | Chief People Officer (CPO) | 3 | 3 | 9 | Medium | Security awareness training bi-annually; VPN mandated; endpoint management (MDM) in place. | Adequate | Chief Information Security Officer (CISO) | 2 | 3 | 6 | Medium | Annual phishing simulation; mandatory device compliance check; introduce culture measurement framework. | Chief Information Security Officer (CISO) | 2026-04-30 | 2025-10-15 | In Progress
TC-010 | Diversity, Equity & Inclusion (DEI) Compliance | Failure to meet gender pay gap reporting obligations or DEI targets triggers reputational damage and talent risks. | Human Resources | Chief People Officer (CPO) | 2 | 3 | 6 | Medium | Annual gender pay gap report published; D&I committee active; unconscious bias training mandatory. | Adequate | Chief People Officer (CPO) | 1 | 3 | 3 | Low | Set measurable DEI targets; publish progress quarterly; integrate DEI into exec scorecards. | Chief People Officer (CPO) | 2026-12-31 | 2025-11-01 | In Progress
TC-011 | Critical Product Defect / Outage | Severe bug in production release causes customer data loss, SLA breach or platform-wide outage. | Product & Engineering | Chief Technology Officer (CTO) | 3 | 4 | 12 | High | Automated test coverage >80%; staged rollout (canary); on-call SRE rotation; incident runbooks. | Adequate | Chief Technology Officer (CTO) | 2 | 3 | 6 | Medium | Increase test coverage to 90%; implement chaos engineering; reduce MTTR to <1hr. | Chief Technology Officer (CTO) | 2026-05-31 | 2025-10-01 | In Progress
TC-012 | Intellectual Property Theft | Theft of proprietary algorithms, source code or trade secrets by competitors or nation-state actors. | Product & Engineering | Chief Information Security Officer (CISO) | 2 | 5 | 10 | Medium | Code repository access controls; DLP on email/USB; NDA for all employees and contractors. | Adequate | Chief Information Security Officer (CISO) | 1 | 4 | 4 | Low | Deploy UEBA for anomalous code access; conduct IP risk assessment; strengthen contractor controls. | Chief Information Security Officer (CISO) | 2026-08-31 | 2025-09-01 | Open
TC-013 | SOC 2 / ISO 27001 Certification Lapse | Failure to maintain security certifications leads to loss of enterprise customer contracts and procurement disqualification. | Compliance | Chief Compliance Officer (CCO) | 3 | 4 | 12 | High | SOC 2 Type II achieved; ISO 27001 surveillance audit scheduled; compliance calendar maintained. | Strong | Chief Compliance Officer (CCO) | 1 | 4 | 4 | Low | Automate evidence collection; maintain continuous compliance posture; schedule Type II renewal 6 months ahead. | Chief Compliance Officer (CCO) | 2026-10-31 | 2025-12-01 | Closed
TC-014 | Disruptive Competitor / Technology Obsolescence | Rapid emergence of a competing platform or paradigm shift (e.g. AI-native tools) erodes market share. | Strategic | Chief Executive Officer (CEO) | 3 | 4 | 12 | High | Quarterly competitive landscape review; R&D budget at 15% of revenue; innovation sprint cycles. | Basic | Chief Executive Officer (CEO) | 3 | 3 | 9 | Medium | Establish innovation lab; conduct annual technology horizon scanning; develop AI product roadmap. | Chief Executive Officer (CEO) | 2026-12-31 | 2025-10-15 | Open
TC-015 | Revenue Concentration Risk | Over-reliance on top-3 customers (>50% ARR) creates existential risk if any customer churns. | Financial | Chief Financial Officer (CFO) | 3 | 5 | 15 | High | Customer success programme; churn early-warning model; NPS tracking monthly. | Basic | Chief Financial Officer (CFO) | 3 | 4 | 12 | High | Diversify customer base; set concentration limit policy (no single customer >20% ARR). | Chief Financial Officer (CFO) | 2026-09-30 | 2025-11-30 | Open
⚡ Inherent Score (I) = Likelihood × Impact ¦ Inherent Rating (J) auto-derived from Score ¦ Residual Score (P) = Residual Likelihood × Residual Impact ¦ Residual Rating (Q) auto-derived — change any input and all scores update instantly

## Roles & Responsibilities
GRC ROLES & RESPONSIBILITIES — RACI MATRIX
R = Responsible A = Accountable C = Consulted I = Informed
ROLE PROFILES
Role | Description | Key Responsibilities
Chief Executive Officer (CEO) | Sets strategic direction, risk appetite and innovation culture. Accountable to the Board for company performance and ESG. | • Strategic risk decision-making • Board & investor risk communication • Innovation & competitive strategy • ESG & sustainability leadership • M&A oversight • Crisis leadership
Chief Technology Officer (CTO) | Owns product engineering, platform reliability, technical architecture and AI/ML strategy. | • Product engineering & SRE • Technical architecture decisions • Platform reliability & SLA • AI/ML product strategy • Tech debt & legacy management • Engineering team leadership
Chief Risk Officer (CRO) | Owns enterprise risk management framework. Provides risk oversight across technology, financial and operational domains. | • ERM framework design • Risk appetite & register maintenance • Board risk reporting • Third-party & supply chain risk • Cyber risk governance • Emerging risk horizon scanning
Chief Information Security Officer (CISO) | Accountable for information security strategy, product security, cloud security and incident response. | • Cyber risk & threat management • Security architecture & standards • SOC 2 / ISO 27001 compliance • Incident response & BCDR • Vendor security due diligence • Security awareness programme
Chief People Officer (CPO) | Responsible for talent acquisition, retention, DEI, remote workforce culture and HR compliance. | • Talent acquisition & retention strategy • DEI programme & gender pay reporting • Remote work policy & culture • Learning & development (AI upskilling) • HR compliance & employment law • Succession planning
Chief Financial Officer (CFO) | Owns financial risk including revenue concentration, fraud, liquidity and financial regulatory compliance. | • Revenue concentration monitoring • Financial controls & audit • Fraud risk management • Budget & forecasting • Investor reporting • Financial regulatory compliance
Chief Compliance Officer (CCO) | Manages regulatory compliance including GDPR, SOC 2, export controls and sector-specific obligations. | • Regulatory compliance calendar • GDPR / privacy programme • SOC 2 / ISO 27001 certification • Export control & sanctions compliance • Policy lifecycle management • Compliance training & awareness
Data Protection Officer (DPO) | Statutory GDPR role. Manages privacy programme, DPIAs, data subject rights and regulatory liaison. | • GDPR Article 30 records • DPIA programme • Data subject rights handling • Privacy by design advisory • Supervisory authority liaison • Cross-border data transfer compliance
IT Director | Responsible for cloud infrastructure, DevOps/SRE, PAM, toolchain security and IT vendor management. | • Cloud infrastructure management • DevOps & CI/CD pipeline security • PAM & access control • IT vendor management • Disaster recovery & BCP • Technology change management
Internal Audit Lead | Provides independent assurance over security controls, financial controls and regulatory compliance posture. | • Annual risk-based audit plan • SOC 2 control testing support • Financial controls assurance • Regulatory compliance audits • Penetration test oversight • Findings & action tracking
RACI MATRIX — KEY GRC ACTIVITIES
GRC Activity | CEO | CTO | CRO | CISO | CFO | CPO | CCO | DPO | IT Dir | Int Audit
Enterprise Risk Framework | I | I | A | C | C | I | C | I | I | C
Risk Appetite Statement | A | C | R | C | C | I | C | I | I | C
Cloud Infrastructure Resilience | I | A | C | C | I | I | I | I | R | C
Software Supply Chain Security | I | C | C | A | I | I | I | I | R | C
Cyber Incident Response | I | C | C | A | I | I | I | I | R | I
Customer Data / GDPR Compliance | I | I | C | C | I | I | R | A | I | C
SOC 2 / ISO 27001 Certification | I | C | C | R | I | I | A | C | R | C
Product Security | I | A | C | R | I | I | I | I | C | C
Talent Acquisition & Retention | I | C | I | I | I | A | I | I | I | I
AI / ML Skills Development | C | A | I | I | I | R | I | I | I | I
DEI & HR Compliance | I | I | I | I | C | A | R | I | I | C
Remote Work Security | I | C | I | A | I | R | I | I | R | I
PAM & Access Control | I | C | C | A | I | I | I | I | R | C
Revenue Concentration Monitoring | A | I | C | I | R | I | I | I | I | C
Financial Controls | I | I | I | I | A | I | C | I | I | R
IP Protection & Trade Secrets | I | C | C | A | I | I | C | I | I | C
Internal Audit Programme | I | I | C | C | C | I | C | I | I | A
Board Risk Reporting | A | I | R | C | C | I | C | I | I | C
A | A: = Accountable
R | A: = Responsible
C | A: = Consulted
I | A: = Informed

## Scoring Methodology
GRC RISK SCORING METHODOLOGY
⚡ Inherent Score = Likelihood × Impact ¦ Residual Score = Residual Likelihood × Residual Impact ¦ All scores recalculate automatically when inputs change
LIKELIHOOD SCALE |  |  | CONTROL EFFECTIVENESS
Score | Rating | Definition | Rating | Reduction | Criteria
5 | Very High | Almost certain — continuous threat; exploited regularly | Strong | 55% | SOC 2 II / ISO 27001 certified; tested; no gaps
4 | High | Likely — expected to occur within 12 months | Adequate | 35% | Controls present; minor gaps; cert in progress
3 | Medium | Possible — could occur within 1–3 years | Basic | 15% | Partial controls; significant gaps; largely manual
2 | Low | Unlikely — may occur within 3–5 years | Weak | 0% | Insufficient controls; critical gaps
1 | Very Low | Rare — less than once in 5 years
THREE LINES OF DEFENCE
IMPACT SCALE |  |  | Line | Owner | Role
Score | Rating | Definition | 1st | Business Unit / Department Leads | Day-to-day risk ownership & control operation
5 | Catastrophic | Existential threat; regulatory closure; loss > £50M | 2nd | CRO / CCO / CISO / HR | Risk framework, policy, oversight & challenge
4 | Major | Material harm; loss £10M–£50M; significant regulatory sanction | 3rd | Internal Audit | Independent assurance over risk & controls
3 | Moderate | Disruption; loss £1M–£10M; regulatory attention
2 | Minor | Limited impact; loss £100K–£1M; manageable
1 | Negligible | Minimal; loss < £100K; quickly resolved
RISK RATING MATRIX (Inherent)
Score | Rating | Required Response
20–25 | Critical | Board escalation within 24 hrs. Emergency treatment plan.
12–19 | High | Escalate to CRO. Active remediation. Review within 30 days.
6–11 | Medium | Assign owner. Treatment plan within 60 days. Quarterly monitoring.
2–5 | Low | Accept or treat. Standard annual review cycle.
1 | Informational | Log and monitor. Annual review.

## Executive Dashboard
GRC EXECUTIVE RISK DASHBOARD — KTECH
Reporting Period: Q1 2026 ¦ Prepared by: Senior GRC Analyst ¦ As of 07 April 2026 ¦ All metrics update automatically from the Risk Register
Total Risks |  |  | Critical / High |  |  | Open Risks | Avg Residual Score
15 |  |  | 2 |  |  | 14 | 7.4
Closed / Accepted |  |  | Overdue Actions |  |  | IT / Tech Risks | HR / People Risks
1 |  |  | 0 |  |  | 7 | 4
RISK DISTRIBUTION BY DOMAIN ⚡ Auto-updates
Domain | Total | Critical | High | Medium | Low
Governance | 1 | 0 | 0 | 1 | 0
Information Technology | 5 | 0 | 0 | 4 | 1
Human Resources | 4 | 0 | 1 | 2 | 1
Product & Engineering | 2 | 0 | 0 | 1 | 1
Compliance | 1 | 0 | 0 | 0 | 1
Financial | 1 | 0 | 1 | 0 | 0
Strategic | 1 | 0 | 0 | 1 | 0
RISK OWNERSHIP SUMMARY ⚡ Auto-updates
Role | Owned | Open | In Progress | Closed | Avg Residual
CTO | 1 | 0 | 1 | 0 | 6
CRO | 1 | 0 | 1 | 0 | 9
CISO | 4 | 3 | 1 | 0 | 7
CPO | 4 | 2 | 2 | 0 | 7.5
CFO | 1 | 1 | 0 | 0 | 12
CCO | 1 | 0 | 0 | 1 | 4

## Heat Map
Risk Prioritisation — Heat Map
KTECH Residual Risk View ¦ Q1 2026
← MORE CONTROLLED VULNERABILITY / LIKELIHOOD LESS CONTROLLED →
IMPACT ↑ | 5 – Catastrophic | TC-002 | TC-003 |  |  |  | RISK RATING LEGEND
| 4 – Major | TC-012 TC-013 | TC-004 TC-005 | TC-007 TC-015 |  |  | HIGH | Residual score 12–19
| 3 – Moderate | TC-010 | TC-006 TC-009 TC-011 | TC-001 TC-008 TC-014 |  |  |  | Escalate to CRO. Active remediation.
| 2 – Minor | [5 empty] | MEDIUM | Residual score 6–11
| 1 – Negligible | [6 empty] | Owner assigned. Quarterly monitoring.
|  | 1 – Rare | 2 – Unlikely | 3 – Possible | 4 – Likely | 5 – Almost Certain | LOW | Residual score 2–5
RISK INDEX | [7 empty] | Accept or treat. Annual review.
Risk ID | Risk Title | Domain | Res. Likelihood | Res. Impact | Residual Score | Rating
TC-001 | Inadequate Enterprise Risk Governance | Governance | 3 | 3 | 9 | Medium
TC-002 | Cloud Infrastructure Failure | Information Technology | 1 | 5 | 5 | Low
TC-003 | Software Supply Chain Attack | Information Technology | 2 | 5 | 10 | Medium
TC-004 | Zero-Day Vulnerability Exploitation | Information Technology | 2 | 4 | 8 | Medium
TC-005 | Customer Data Breach (GDPR/CCPA) | Information Technology | 2 | 4 | 8 | Medium
TC-006 | Privileged Access & Insider Threat | Information Technology | 2 | 3 | 6 | Medium
TC-007 | Developer Talent Attrition | Human Resources | 3 | 4 | 12 | High
TC-008 | AI / ML Skills Gap | Human Resources | 3 | 3 | 9 | Medium
TC-009 | Remote Work Security & Culture Risk | Human Resources | 2 | 3 | 6 | Medium
TC-010 | Diversity, Equity & Inclusion (DEI) Compliance | Human Resources | 1 | 3 | 3 | Low
TC-011 | Critical Product Defect / Outage | Product & Engineering | 2 | 3 | 6 | Medium
TC-012 | Intellectual Property Theft | Product & Engineering | 1 | 4 | 4 | Low
TC-013 | SOC 2 / ISO 27001 Certification Lapse | Compliance | 1 | 4 | 4 | Low
TC-014 | Disruptive Competitor / Technology Obsolescence | Strategic | 3 | 3 | 9 | Medium
TC-015 | Revenue Concentration Risk | Financial | 3 | 4 | 12 | High